## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Vighnesh Nikhil | 2026-03-28 | CORS error when connecting frontend to backend | Sprint 4 | Backend Team | Integration | Enabled CORS middleware in FastAPI | 2026-03-28 | Closed | Issue resolved successfully
2 | Vighnesh Nikhil | 2026-03-27 | Session ID not generated correctly on start | Sprint 3 | Backend Team | Functional | Fixed API endpoint and method (POST) | 2026-03-27 | Closed | Session working properly
3 | Vighnesh Nikhil | 2026-03-28 | Invalid Patient ID causing backend crash | Sprint 4 | Backend Team | Logic | Added proper validation and fallback response | 2026-03-28 | Closed | Stable response ensured
4 | Vighnesh Nikhil | 2026-03-29 | Voice input not working in browser | Sprint 4 | Frontend Team | UI/Integration | Updated SpeechRecognition handling and permissions | 2026-03-29 | Closed | Voice input functioning
5 | Vighnesh Nikhil | 2026-03-29 | UI not showing response properly | Sprint 4 | Frontend Team | UI | Fixed response rendering in HTML | 2026-03-29 | Closed | UI updated successfully
6 | Vighnesh Nikhil | 2026-03-25 | IVR menu routing not working correctly | Sprint 2 | Backend Team | Logic | Fixed menu handling logic | 2026-03-25 | Closed | Routing corrected