## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Product Backlog
| Table 1 | Product Backlog
Sprint Backlog
| Table 1 | Sprint Backlog
Stand up Meeting
| Table 1 | Stand up Meeting
Retrospection
| Table 1 | Retrospection

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a system analyst, I want to study the working of traditional IVR systems so that I can understand how user interaction flows are structured. | MUST HAVE | Research material and documentation | Backend Team | Completed
Sprint 1 | Sprint 1 | US002 | s a developer, I want to design the system architecture for a hospital IVR service so that lab-related queries can be handled efficiently. | MUST HAVE | System design planning | Backend Team | Completed
Sprint 2 | Sprint 2 | US003 | As a backend developer, I want to implement a FastAPI backend for the IVR system so that user requests can be processed programmatically. | MUST HAVE | API framework setup | Backend Team | Completed
Sprint 2 | Sprint 2 | US004 | As a developer, I want to create menu-based IVR options for hospital lab services so that users can retrieve information using keypad inputs. | MUST HAVE | Backend API logic | Backend Team | Completed
Sprint 3 | Sprint 3 | US005 | As an AI developer, I want to implement intent detection for conversational input so that users can interact with the IVR using natural language instead of keypad inputs. | SHOULD HAVE | NLP logic implementation | Backend Team | Completed
Sprint 3 | Sprint 3 | US006 | As a developer, I want to extract patient ID information from user input so that report status can be retrieved automatically. | COULD HAVE | Pattern matching logic | Backend Team | Completed
Sprint 4 | Sprint 4 | US007 | As a developer, I want to integrate conversational AI with the existing IVR backend so that both conversational and keypad interactions are supported. | MUST HAVE | Backend integration | Backend Team | Completed
Sprint 4 | Sprint 4 | US008 | As a developer, I want to test the IVR workflows and conversational interface so that the system performs reliably during demonstrations. | SHOULD HAVE | System testing | Backend Team | Completed
Note on F1: Sumeet Kumar Barua08: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Research existing IVR systems and analyze workflow structure | 2025-02-02 | 2026-02-05 | Backend1 | Research | Done | 6 | bar: Day 2 to Day 3; Day 5 to Day 6
US002 | T2 | Document architecture for hospital IVR system | 2026-02-06 | 2026-02-10 | Backend2 | Documentation | Done | 8 | bar: Day 3 to Day 6
US003 | T3 | Setup FastAPl project structure and backend environment | 2026-02-11 | 2026-02-15 | Backend1 | Backend development | Done | 10 | bar: Day 2 to Day 5
US004 | T4 | Implement menu-based IVR logic for lab services | 2026-02-16 | 2026-02-20 | Backend2 | Backend development | Done | 12 | bar: Day 1 to Day 2; Day 4; Day 6 to Day 9
US005 | T5 | Develop conversational intent detection logic | 2025-03-05 | 2026-03-08 | Backend1 | AI Integration | Done | 8 | bar: Day 3 to Day 6
US006 | T6 | Implement patient ID extraction using pattern matching | 2026-03-09 | 2026-03-12 | Backend2 | Backend logic | Done | 6 | bar: Day 5 to Day 7
US007 | T7 | Integrate conversational interface with IVR menu backend | 2026-03-13 | 2026-03-15 | Backend1 | Integration | Done | 10 | bar: Day 7 to Day 11
Note on D2: Sumeet Kumar Barua08: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Sumeet Kumar Barua08: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: Sumeet Kumar Barua08: This is the total task estimated in hours for all the user stories
Note on J3: Sumeet Kumar Barua08: Pending effort hours after completion of day 1 work
Note on K3: Sumeet Kumar Barua08: Pending effort hours after completion of day 2 work
Note on L3: Sumeet Kumar Barua08: Pending effort hours after completion of day 3 work
Note on M3: Sumeet Kumar Barua08: Pending effort hours after completion of day 4 work
Note on N3: Sumeet Kumar Barua08: Pending effort hours after completion of day 5 work
Note on O3: Sumeet Kumar Barua08: Pending effort hours after completion of day 6 work
Note on P3: Sumeet Kumar Barua08: Pending effort hours after completion of day 7 work
Note on Q3: Sumeet Kumar Barua08: Pending effort hours after completion of day 8 work
Note on R3: Sumeet Kumar Barua08: Pending effort hours after completion of day 9 work
Note on S3: Sumeet Kumar Barua08: Pending effort hours after completion of day 10 work
Note on T3: Sumeet Kumar Barua08: Pending effort hours after completion of day 11 work
Note on U3: Sumeet Kumar Barua08: Pending effort hours after completion of day 12 work
Note on V3: Sumeet Kumar Barua08: Pending effort hours after completion of day 13 work
Note on W3: Sumeet Kumar Barua08: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty understanding IVR interaction flow | Studied documentation and analyzed sample IVR systems
Sprint 2 | Day 3 | Backend endpoint retuning incorrect response | Debugged FastAPI routes and corrected request structure
Sprint 3 | Day 2 | Conversational input not detecting certain intents | Expanded keyword detection and improved intent rules
Sprint 3 | Day 4 | Patient ID extraction failing for some inputs | Updated regex pattern to capture numeric IDs
Sprint 4 | Day 1 | Integration issues between conversational logic and IVR backend | Adjusted endpoint routing and tested conversational flow

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-02-02 | 2026-02-16 | Backend Team | Documenting architecture clearly | Spending too much time on unstructured research | Team discussion for planning | Created shared architecture notes
2 | 2 | 2026-02-17 | 2026-03-02 | Backend Team | Implementing backend modules step-by-step | Writing untested code | API testing during development | Introduced regular backend testing
3 | 3 | 2026-03-03 | 2026-03-16 | Backend Team | Improving conversational interaction design | Ignoring edge cases in input | Enhancing intent detection logic | Added additional conversational rules
4 | 4 | 2026-03-17 | 2026-03-30 | Backend Team | Preparing system documentation earlier | Rushing integration at the end | Regular team sync meetings | Scheduled weekly review meetings